## DIR_Template
#VALUE!
Project Name | [13 empty] | Reason For Issue | Code | Reason For Issue | Code | Reason For Issue | Code | Reason For Issue | Code |  | ID | #1 |  |  | #2 |  |  | #3 |  |  | #4
[14 empty] | Design Development Issue | DI | Listed Building Consent | LB | Pricing Issue | PI | Construction Issue | CT |  | STAGE | Stage 3 |  |  | Stage 3 |  |  | Stage 3 |  |  | Stage 3
TPB Project Number | [13 empty] | Stage Issue | SI | Building Control Submission | BC | Tender Issue | TI | Handover Issue | HI |  | Issue date | 2026-05-30 |  |  | 2026-05-30 |  |  | 2026-05-30 |  |  | 2026-05-30
[14 empty] | Planning Submission | PS | Authority Submission | AS | Contract Issue | CI | Record Issue | RI
Project Code |  | Originator |  | Functional Breakdown |  | Spatial Breakdown |  | Form |  | Discipline |  | Number |  | Title | [5 empty] | Current Revision | Current Revision Date | Paper Size | Scale | Revision | Suitability | Reason For Issue | Revision | Suitability | Reason For Issue | Revision | Suitability | Reason For Issue | Revision | Suitability | Reason For Issue
DRAWINGS
TMPLT | - | TPB | - | L1 | - | ZZZ | - | DR | - | AR | - | 000003 | - | Diagram, Level All Project Symbols | [5 empty] | P02 | 19/06/2026 | A0 | NTS | P01 | S1 | DI
TMPLT | - | TPB | - | L3 | - | ZZZ | - | DR | - | AR | - | 000004 | - | Drawing list, Story board & Drawing register | [5 empty] | P03 | 30/10/2026 | A0 | NTS |  |  |  | P01 | S2 | DI
TMPLT | - | TPB | - | L2 | - | ZZZ | - | DR | - | AR | - | 007101 | - | Existing Second Floor - Demolition Plan - All Zones | [5 empty] | P03 | 30/06/2026 | A0 | 1:100
TMPLT | - | TPB | - | L0 | - | ZZZ | - | DR | - | AR | - | 031001 | - | Existing Ground Floor - General Arrangement Plan - All Zones | [5 empty] | C01 | 13/05/2026 | A0 | As Indicated
TMPLT | - | TPB | - | L3 | - | ZZZ | - | DR | - | AR | - | 031008 | - | Existing Third Floor - General Arrangement Plan - All Zones | [5 empty] | P04 | 19/06/2026 | A0 | 1:200
TMPLT | - | TPB | - | L0 | - | ZZZ | - | DR | - | AR | - | 061001 | - | Existing Ground Floor - General Arrangement Plan - All Zones | [5 empty] | P04 | 30/06/2026 | A0 | 1:100
TMPLT | - | TPB | - | L0 | - | ZZZ | - | DR | - | AR | - | 071001 | - | Existing Ground Floor - Demolition Plan - All Zones | [5 empty] | P01 | 08/03/2026 | A0 | 1:100
TMPLT | - | TPB | - | L2 | - | ZZZ | - | DR | - | IN | - | 201001 | - | Second Floor - General Arrangement Plan Zone 4 Multi-Purpose Space | [5 empty] | P03 | 19/06/2026 | A0 | 1:100
TMPLT | - | TPB | - | L6 | - | ZZZ | - | DR | - | IN | - | 201002 | - | Sixth Floor - General Arrangement Plan Zones 3 & 4 | [5 empty] | P04 | 19/06/2026 | A0 | 1:100
TMPLT | - | TPB | - | ZZ | - | ZZZ | - | DR | - | IN | - | 203001 | - | General Arrangement Sections - Levels 01 & 02 - All Zones | [5 empty] | C01 | 09/11/2026 | A0 | 1:100
TMPLT | - | TPB | - | ZZ | - | ZZZ | - | DR | - | IN | - | 203002 | - | General Arrangement Sections - Levels 03 & 06 - All Zones | [5 empty] | P03 | 08/03/2026 | A0 | 1:100
TMPLT | - | TPB | - | L1 | - | ZZZ | - | DR | - | AR | - | 204001 | - | First Floor - Tiered Auditorium - Zone 1 - Sheet 1 | [5 empty] | P03 | 30/06/2026 | A0 | 1:100
TMPLT | - | TPB | - | L1 | - | ZZZ | - | DR | - | AR | - | 204002 | - | First Floor - Tiered Auditorium - Zone 1 - Sheet 2 | [5 empty] | P06 | 19/06/2026 | A0 | 1:100
TMPLT | - | TPB | - | L6 | - | ZZZ | - | DR | - | IN | - | 204003 | - | General Arrangement Studio Room - Level 06 - Zone 01 Sheet 03 | [5 empty] | P07 | 30/06/2026 | A0 | 1:100
MODELS
REPORTS
Recipients
Name |  |  |  | Company
Jordan Lane |  |  |  | TPB | [19 empty] | AF, Aconex
Name 02 |  |  |  | Company 02
Name 03 |  |  |  | Company 03
Name 04 |  |  |  | Company 04
Name 05 |  |  |  | Company 05
Name 06 |  |  |  | Company 06
Name 07 |  |  |  | Company 07
Name 08 |  |  |  | Company 08
Name 09 |  |  |  | Company 09
Name 10 |  |  |  | Company 10
Name 11 |  |  |  | Company 11